## Team 1
Date | Duration (h) | Topic | In-charge | Status
2025-01-09 | 8 | Project Kick-off + Requirement Gathering | All team | Started
2025-01-15 | 8 | Develop Back-End Architecture | Hung | Started
2025-01-10 | 8 | Requirement Analysis + Create SRS | All team | Planned
2025-01-15 | 8 | Review and Update SRS | All team | Planned
2025-02-05 | 8 | Create Use Case Diagrams and Process Flows | All team | Planned
2025-02-06 | 8 | Database Design | All team | Planned
2025-02-05 | 8 | Authentication and Authorization Implementation | Hung | Planned
2025-02-10 | 8 | Develop Product Management |  | Planned
2025-02-15 | 8 | Develop Cart Management |  | Planned
2025-02-25 | 8 | Develop Order Management |  | Planned
2025-02-28 | 8 | Develop User Management (Reset Password) |  | Planned
2025-03-02 | 8 | Develop Dashboard |  | Planned
2025-03-03 | 8 | Integration of Product and Order Management |  | Planned
2025-03-04 | 8 | Integration of Back-End and Front-End |  | Planned
2025-03-11 | 8 | Review + Fix Issues (Round 1) |  | Planned
2025-03-16 | 8 | Create Test Plan + Test Case |  | Planned
2025-03-21 | 8 | Execute Testing Phase (Part 1) |  | Planned
2025-03-24 | 8 | Execute Testing Phase (Part 2) |  | Planned
2025-03-20 | 8 | User Acceptance Testing (UAT) |  | Planned
2025-03-24 | 8 | Review Test Results + Bug Fixing |  | Planned
2025-03-25 | 8 | Final Bug Fixes + System Optimization |  | Planned
2025-03-30 | 8 | Prepare Final Report |  | Planned
Tên đề tài: | Xây dựng website bán hàng bàn ghế
Dương Đức Hùng
Trương Công Thảo Nguyên
Nguyễn Thị Thu Hà
Nguyễn Đình Hoàng Hải