## W1
PROJECT REPORT
Group | Furniture Team
Week | 16/02/2025 - 23/02/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Compeled project plan | All Team | Completed
| Create SRS | All Team | Completed
| Create DashBoard for admin | Nguyên | In Progress
| Complete DashBoard for admin | Nguyên | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Define database design | All Team | 2025-08-02 | Decide database type: SQL
| Define layout & script | All Team | 2025-08-02
| Complete DashBoard for admin | Nguyên | 15/2/2025
| Create CRUD product | Nguyên | 12/2/202
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes